## Hoja1
Tasks | Planned start | royal start | planned conclusion | Assigned Person | Assigned effort | Grades
Development of the new system | w1 | w1 | w6 | M,J,S,O,Y,D | 5 | Give priority to essential activities and respect stipulated dates, leaving a margin of time for any inconvenience.
On-site tests | w5 | w5 | w8 | J,Y | 2
Database Implementation | w5 | w5 | w10 | D,S | 4
User interface design | w9 | w9 | w10 | M,O | 3
Connection and implementation in-office test equipment | w9 | w9 | w12 | D,S | 5
Long deployment under system usage load | w7 | w7 | w15 | M,J,S,O,Y,D | 2
Documentation and delivery to company | w15 | w15 | w16 | M,O | 4